## Bobek
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-09-18 | Design | Project-Meeting | 0:30 | 0:30
SUM |  |  | 0:30 | 0:30

## Bergler
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-09-18 | Design | Project-Meeting | 0:30 | 0:30
SUM |  |  | 0:30 | 0:30

## Janeczek
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-09-18 | Design | Project-Meeting | 0:30 | 0:30
2014-09-10 | Recherche | Finding an appropriate SNMP-Framework | 3:00 | 2:00 | SNMP4J and Mibble are the chosen ones
2014-09-25 | Recherche | Gathering essential information | 3:00 | 6:30 | We haven't had an introduction to SNMP in the 4th grade, so it took a while to fully understand the SNMP basics
2014-10-27 | Implementation | Implementing the last Basic Tasks | 4:00 | 3:30 | still ongoing, though
2014-10-28 | Implementation | Getting into the Mibble API and working with MIB-Files | 3:00 | 3:23 | It took longer than expected
2014-10-29 | Implementation | Reading out of the "NETSCREEN-SMI.mib" and "NS-POLICY.mib" files | 2:00 | 2:22 | Reading wasn't the problem. I had some issues with Eclipse adding the newly created mib/ directory to the Build-Path
2014-10-30 | Implementation | Reading the policies of the Firewall via the SnmpWalk tool and implementing it in our application | 3:00 | 4:01
SUM |  |  | 18:30 | 22:16

## Mair
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-09-18 | Design | Project-Meeting | 0:30 | 0:30
2014-10-27 | Implementation | SNMPv2 Reader Impl. | 5:00 | 4:00 | still ongoing, though
2014-10-28 | Implementation | Mibble API | 4:00 | 3:23 | Mibble is one son of a API
2014-10-29 | Implementation | Reading out of Mib-Files | 2:00 | 2:22
SUM |  |  | 11:30 | 10:15

## Oezsoy
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-09-18 | Design | Project-Meeting | 0:30 | 0:30
SUM |  |  | 0:30 | 0:30

## SUM
Working Hours
| NAME | ESTIMATION | ACTUAL
| Bergler | 0:30 | 0:30
| Bobek | 0:30 | 0:30
| Janeczek | 18:30 | 22:16
| Mair | 11:30 | 10:15
| Oezsoy | 0:30 | 0:30
| SUM | 30:00 | 32:31