## Bobek
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
09.18.2014 | Design | Project-Meeting | 0:30 | 0:30
09.18.2014 | Design | Project-Meeting | 0:30 | 0:30
09.25.2014 | Design | User-Stories | 2:00 | 2:00
2014-02-10 | Design | GUI - Erste Konzepte | 1:30 | 2:00
2014-10-09 | Design, Recherche | GUI-Mockups; JavaFX: Recherche, Pros/Cons; | 3:00 | 5:30
10.16.2014 | Implementation | GUI-Erstellung(Pop-ups) | 5:00 | 3:30
10.26.2014 | Recherche | Recherche nach geeigneten GUI-Testing-Tool | 1:00 | 4:00
10.30.2014 | Implementation | Tabelle befüllen mit Daten | 3:00 | 4:00
10.31.2014 | Implementation | Tabelle befüllen mit Daten | 1:00 | 4:30
SUM |  |  | 12:30 | 14:00

## Bergler
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-09-18 | Design | Project-Meeting | 0:30 | 0:30
09.18.2014 | Design | Creating rough UML-Draft | 2:00 | 2:31
09.20.2014 | Recherche | Figuring out the required components for SNMP | 2:00 | 2:00
09.21.2014 | Recherche | Figuring out the required components for the program | 2:00 | 2:00
09.21.2014 | Design | Overhauling the UML | 1:00 | 1:00
09.22.2014 | Design | Finishing the UML | 3:00 | 4:00 | This shouldve been done way earlier...
09.23.2014 | Implementation | Autogenerating the Classes, Codecleanup, Implementing the Interfaces, Setting up relations | 3:00 | 3:00
09.27.2014 | Implementation | Teaching my Team where to put what, Researching | 2:00 | 2:00
10.31.2014 | Implementation | Creating Properties, Debugging some stuff | 3:00 | 3:00 | not finished...
SUM |  |  | 18:30 | 20:01

## Janeczek
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-09-18 | Design | Project-Meeting | 0:30 | 0:30
2014-09-10 | Recherche | Finding an appropriate SNMP-Framework | 3:00 | 2:00 | SNMP4J and Mibble are the chosen ones
2014-09-25 | Recherche | Gathering essential information | 3:00 | 6:30 | We haven't had an introduction to SNMP in the 4th grade, so it took a while to fully understand the SNMP basics
2014-10-27 | Implementation | Implementing the last Basic Tasks | 4:00 | 3:30 | still ongoing, though
2014-10-28 | Implementation | Getting into the Mibble API and working with MIB-Files | 3:00 | 3:23 | It took longer than expected
2014-10-29 | Implementation | Reading out of the "NETSCREEN-SMI.mib" and "NS-POLICY.mib" files | 2:00 | 2:22 | Reading wasn't the problem. I had some issues with Eclipse adding the newly created mib/ directory to the Build-Path
2014-10-30 | Implementation | Reading the policies of the Firewall via the SnmpWalk tool and implementing it in our application | 3:00 | 4:01
2014-10-31 | Implementation | Using SSH for CRUD functions | 2:00 | 4:46 | SSH via PuTTy works, Java Implementation is buggy
SUM |  |  | 20:30 | 27:02

## Mair
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-09-18 | Design | Project-Meeting | 0:30 | 0:30
2014-09-25 | Design | Collecting information for SNMP and downloading the required tools for the connection to the router | 4:00 | 4:00
2014-10-02 | Design | Information Gathering | 3:00 | 6:30 | Problems with understanding
2014-10-27 | Implementation | SNMPv2 Reader Impl. | 5:00 | 4:00 | still ongoing, though
2014-10-28 | Implementation | Mibble API | 4:00 | 3:23 | Mibble is one son of an API
2014-10-29 | Implementation | Reading out of Mib-Files | 2:00 | 2:22
2014-10-30 | Implementation | Reading with SNMP | 3:00 | 5:04 | Problems with understanding SNMP-Code
2014-10-31 | Implementation | Reading all Infos with SNMP | 2:00 | 4:50 | Finally getting everything
SUM |  |  | 23:30 | 30:39

## Oezsoy
Working Hours
DATE | PHASE | TASK | ESTIMATION | ACTUAL | COMMENT
2014-09-18 | Design | Project-Meeting | 0:30 | 0:30
09.20.2014 | Design | Creating a GUI-Concept | 0:30 | 1:30
09.25.2014 | Recherche | Doing a recherche about JavaFX | 1:00 | 3:35
2014-10-02 | Implementation | Implementing the 1st version of the GUI | 4:00 | 4:20
2014-03-10 | Design | Collecting information for SNMP and downloading the required tools for the connection to the router | 4:00 | 3:00 | The downloads took more time than estimated
2014-10-09 | Implementation | Implementing all of the Pop-Up-Windows | 1:00 | 3:00
10.27.2014 | Recherche | Recherche about GUIdancer (advantages and disadvantages) | 0:30 | 1:25 | It was difficult to find useful information
10.28.2014 | Recherche | Recherche about LineChart for JavaFX (How to implement a LineChart in JavaFX) | 0:15 | 1:00
10.29.2014 | Implementation | Implementing a LineChart with test data in JavaFX | 2:00 | 5:00 | The implementation of the LineChart was more difficult than estimated
10.30.2015 | Implementation | Optimization of the LineChart with an IntervalRefresher-Thread | 2:00 | 6:00 | The refreshing of the interval didn't work like it should work to
10.31.2016 | Implementation | Debugging the Interval-Refreshing of the LineChart | 3:00 | 5:15 | not finished yet …
SUM |  |  | 18:45 | 34:35

## SUM
Working Hours
| NAME | ESTIMATION | ACTUAL
| Bergler | 18:30 | 20:01
| Bobek | 12:30 | 14:00
| Janeczek | 20:30 | 27:02
| Mair | 23:30 | 30:39
| Oezsoy | 18:45 | 34:35
| SUM | 44:00 | 94:42